## Planned Changes
TDL - Planning for Changes Register
|  | Issue No: | 1
Title: | Planning for Changes | Date Issued: | 3rd May 2017
Procedure No: | TDL-003 | Date Reviewed: | 23rd September 2020
Process Owner: | Alex Kempson
Classification: | Confidential
This register is to identify any potential changes to the QMS and ISMS in a planned manner
Date Identified | Purpose of Change | Potential Consequence | How does the change affect the QMS and ISMS | Responsibility | Resources | Timescale | Identified Risk(s) | Conclusion | Completed By | Date | Status
2020-12-01 | Scottish partner has given notice | Not able to fulfil deliveries/collections in Scotland for our customers. | TDL's Performance Supplier Change | Alison Pickett | Alison Pickett Steve Pickett Debbie Jones Iain Jackson John Kavanagh | 2021-01-01 | Not able to fulfil deliveries/collections in Scotland for our customers. New partner may not offer the same price/service and reliability.

## Completed Changes
TDL - Completed Planning for Changes Register
|  | Issue No: | 1.1
Title: | Completed Planning for Changes | Date Issued: | 17th April 2017
Procedure No: |  | Date Reviewed: | 15th June 2020
Process Owner: | Kate Quaye
Classification: | Confidential
Date Identified | Purpose of Change | Potential Consequence | How does the change affect the QMS | Responsibility | Resources | Timescale | Identified Risk(s) | Conclusion | Completed By | Date | Status
2017-09-01 | Introduction of R2C to manage Fleet and Assets Maintenance | Automation of fleet maintenance schedules and all vehicle/equipment assets, electronical storage of all maintenance schedules, tracking of defect reporting, financial reporting. | Improvement in management of fleet and also services supplied to small number of customers. Automation of asset maintenance management. | Alison Pickett | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 6 months - implementation required beginning of February 2018 | Financial reporting not aligned to TDL fiscal calendar. Unauthorised access to tablets/mobiles to report defects - acceptable risk. | Implemention to proceed. Financial reported completed on fiscal period days. Implementation completed succesfully although complexity of user access for Workshop and Operators greater than initially understood. | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2018-02-01 | Implemented.
2018-03-01 | Re-organisation of TDL Management Level Staff. | Additional middle Management Staff, financial cosequences of additional staff. | For both systems, the new staff members will be assuming responsibilities for many of the processes, policies and procedures. Improvement in management of documented systems (additional focus on ISO). | Alison Pickett | Senior Management Staff | To be in place July 2018 | Change Management with existing staff (resistance to the changes), lack of TDL knowledge for new staff members. Risk of not settling in to new role, or ot achieving TDL expectations, risk of discovery (unknown facts about new employee found after employment). | Still in progress - probationary 6-month period for all new Management members. | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2018-07-01 | Implemented.
2018-04-01 | Transition of Payroll from internal HR organisation to external supplier (Kaisen). (Being implemented by H&B Group). | Failed/incorrect wage payments, personal information available external to H&B Group. Disruption to staff, eg wage slips change-over. | QMS - Employee satisfaction and payroll. ISMS - Personnel information being transmitted to external provider. Risk assessment has been requested from H&B Group. | H&B Group / IT Group Manager / HR Group Manager / Group Financial Director | H&B Group resources, TDL Operations Director | August 2018 wages to be completed by Kaisen. | Payroll failure, incorrect payments, personal information available to non-authorised personnel, no internal resource as a point of contact. | In progress. First payments completed at end of August 2018 and there were issues. | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2019-02-01 | Implemented.
2018-04-01 | New Customer introduction - PWS | Additional depots required to support implementation of later phases, extension of Operating licence for additional vehicles, 3rd party software integration with TDL systems | Additional processes will be required for operating out of the new depots | Alison Pickett | Alison Pickett, Alex Kempson, Susan O'Boyle, | To be completed in three phases | More vehicles within the fleet could lead to higher charges for maintenance and repairs - | All three phases complete | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2019-02-01 | Implemented.
Nox-19 | New Customer introduction - Kudos through SCS | 3rd party software integration with TDL systems. | Additional processes will be required. Being managed by current staff levels - performance could be effected | Alison Pickett | Alison Pickett Ian Parry Iain Jackson John Kavanagh | 2020-01-01 | More vehicles within the fleet could lead to higher charges for maintenance and repairs - | Kudos up and running | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2019-05-01 | Implemented.
2020-03-01 | New Customer introduction - WilsonArt | Additional depots required to support implementation of later phases, extension of Operating licence for additional vehicles, 3rd party software integration with TDL systems | Additional processes will be required for operating out of the new depots | Alison Pickett | Alison Pickett Ian Parry Iain Jackson John Kavanagh | 2020-06-01 | More vehicles within the fleet could lead to higher charges for maintenance and repairs - | Wilsonart up and running | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2020-07-01 | Implemented.
2020-04-01 | New Customer introduction - GAP | Supply of sweets across the Island - do we have enough resource i.e drivers/vehicles in the IOM to deal with influct. | Customer demands/service | Alison Pickett | Alison Pickett Ian Parry Iain Jackson Jim Neil | 2020-06-01 | More vehicles within the fleet could lead to higher charges for maintenance and repairs - | Gap up and running | Alison Pickett, Alex Kempson, Susan O'Boyle, Brian Wade | 2020-06-01 | Implemented.